## GovFlow_Sprint_Board
ID | Epic | Task | Description | Owner | Priority | Status | Est (hrs) | Due | Dependencies | Agent | Component | Track
GF-01 | Setup | Provision Cloud & Repos | Create repos, set env vars, enable APIs (Firestore, Storage), local .env. | Owner | High | Todo | 2 | 2025-10-03 |  | — | Cloud/Infra | Infra
GF-02 | Policy RAG | Prepare Policy Corpus | Collect 3–5 pages of permit policy PDF and chunk to embeddings. | Owner | High | Todo | 1.5 | 2025-10-03 | GF-01 | PolicyReasoner | Data | Civic Intelligence
GF-03 | Backend | ADK Project Skeleton | Create agents: Intake, Validation, PolicyReasoner, DecisionDrafter, HumanReview, Comms, Audit. | Owner | High | Todo | 3 | 2025-10-03 | GF-01 | All | Backend | Civic Intelligence
GF-04 | Frontend | Citizen Portal Form | Build Next.js form (name, email, address, business type, file upload). | Owner | High | Todo | 2 | 2025-10-03 | GF-01 | — | Frontend | Civic Intelligence
GF-05 | Frontend | Status Timeline | Citizen status page with steps: Received→Validated→Under Review→Decision. | Owner | Medium | Todo | 1.5 | 2025-10-03 | GF-04 | — | Frontend | Civic Intelligence
GF-06 | Frontend | Reviewer Console | Case view: docs, checklist with citations, AI rec, Approve/Request Info/Deny. | Owner | High | Todo | 3 | 2025-10-03 | GF-03 | — | Frontend | Civic Intelligence
GF-07 | Backend | Mock Services | Mock business registry & address validation endpoints. | Owner | Medium | Todo | 1 | 2025-10-03 | GF-03 | Validation | Backend | Civic Intelligence
GF-08 | Backend | RAG Integration | Embed policy, implement vector search & checklist JSON output. | Owner | High | Todo | 2.5 | 2025-10-03 | GF-02,GF-03 | PolicyReasoner | Backend | Civic Intelligence
GF-09 | Backend | Decision Drafting | Compose determination JSON with rationale, risks, uncertainty. | Owner | High | Todo | 1.5 | 2025-10-03 | GF-08 | DecisionDrafter | Backend | Civic Intelligence
GF-10 | Backend | Human-in-the-Loop | Wire reviewer action to update case + trigger comms. | Owner | High | Todo | 1 | 2025-10-03 | GF-06,GF-09 | HumanReview | Backend | Civic Intelligence
GF-11 | Backend | Comms & Letters | Generate plain-language status + decision letter (PDF or HTML). | Owner | Medium | Todo | 1.5 | 2025-10-03 | GF-10 | Comms | Backend | Civic Intelligence
GF-12 | Quality | Audit & Metrics | Log prompts, sources, outcomes. Track TTV, automation rate, coverage. | Owner | Medium | Todo | 1 | 2025-10-03 | GF-03,GF-10 | Audit | Backend | Civic Intelligence
GF-13 | DX/Docs | Demo Script & Slides | 2-min script, 3 slides (problem, architecture, impact). | Owner | Medium | Todo | 1 | 2025-10-03 |  | — | Docs | Enablement
GF-14 | Quality | Golden Path Tests | Approve / Deny / Needs Info fixtures; add retry & fallback cases. | Owner | Medium | Todo | 1 | 2025-10-03 | GF-08,GF-09 | All | QA | Civic Intelligence